## README
GRC Calendar 2026
Purpose | A practical governance, risk and compliance operating calendar for CIO/CISO/GRC teams.
How to use | Assign owners, adjust dates to your regulatory calendar, and review upcoming items in monthly leadership meetings.
Best fit | Mid-sized organizations that need a lightweight rhythm for GRC, third-party risk, resilience, and board reporting.
Important note | This is a planning aid, not legal advice. Align it with your exact sector, jurisdictions, regulators, and internal policies.
Included sheets | GRC Calendar 2026, Tool Backlog, Cadence Model

## GRC Calendar 2026
Due date | Month | Cadence | Activity | Primary owner | Framework / driver | Output / evidence | Priority | Status | Notes
2026-01-15 | January | Annual | Confirm GRC operating calendar, reporting cadence, and control owners | CISO / GRC Lead | ISO 27001, NIS2, DORA, internal governance | Approved GRC calendar and RACI | High | Planned | Run before annual planning locks.
2026-01-31 | January | Annual | Refresh risk appetite, risk taxonomy, and board-level cyber risk themes | CISO / Enterprise Risk | Board governance, ISO 27001 clause 6 | Updated risk appetite and top risk themes | High | Planned | Useful input for board reporting.
2026-02-15 | February | Quarterly | Update information asset and critical service inventory | IT Risk / Service Owners | NIS2, DORA, ISO 27001 A.5.9 | Inventory export and owner attestation | High | Planned | Include outsourced and SaaS dependencies.
2026-02-28 | February | Quarterly | Review critical supplier list and tiering | TPRM Lead / Procurement | NIS2 supply chain, DORA ICT third-party risk | Critical supplier register | High | Planned | Check concentration and nth-party dependencies.
2026-03-15 | March | Quarterly | Review open audit findings, risk acceptances, and remediation aging | GRC Lead / Control Owners | Internal audit, ISO 27001 improvement | Remediation tracker and overdue actions | High | Planned | Highlight aging exceptions for leadership.
2026-03-31 | March | Quarterly | Prepare Q1 cyber and GRC board report | CISO | Board reporting, NIS2 management accountability | Board pack and decision log | High | Planned | Focus on decisions, not operational noise.
2026-04-15 | April | Semi-annual | Run access governance review for privileged and critical business systems | IAM Lead / System Owners | ISO 27001 A.5.15, A.5.18 | Access review evidence and exceptions | High | Planned | Include third-party and admin accounts.
2026-04-30 | April | Quarterly | Test incident escalation and regulatory notification workflow | Security Operations / Legal | NIS2, DORA incident reporting | Exercise results and improvement actions | High | Planned | Tabletop is enough if evidence is captured.
2026-05-15 | May | Annual | Review cybersecurity policies and control ownership | CISO / Policy Owners | ISO 27001 policy framework | Policy review log and approvals | Medium | Planned | Prioritize policies with audit relevance.
2026-05-31 | May | Quarterly | Review vulnerability and patch SLA performance | Security Operations / IT Operations | ISO 27001 A.8.8, operational resilience | Patch KPI report and exceptions | High | Planned | Show trend and unresolved critical items.
2026-06-15 | June | Semi-annual | Validate backup, recovery, and resilience evidence | IT Operations / BCM | DORA, NIS2, ISO 27001 A.5.30 | Recovery test record and gaps | High | Planned | Connect to critical services.
2026-06-30 | June | Quarterly | Prepare Q2 board report and regulatory readiness update | CISO / GRC Lead | Board governance, compliance readiness | Board pack and readiness heatmap | High | Planned | Include supplier and incident-readiness view.
2026-07-15 | July | Quarterly | Refresh AI / shadow IT register | CIO / CISO / Data Governance | AI governance, data protection, third-party risk | AI use case register | Medium | Planned | Capture owner, data type, provider, approval state.
2026-07-31 | July | Quarterly | Review security awareness and phishing metrics | Security Awareness Lead | ISO 27001 A.6.3, management reporting | Awareness KPI report | Medium | Planned | Tie poor results to targeted actions.
2026-08-15 | August | Quarterly | Review supplier incidents, risk signals, and watchlist | TPRM Lead / Security Operations | Continuous monitoring, NIS2 supply chain | Supplier watchlist and actions | High | Planned | Use public incidents, ratings, questionnaires, issues.
2026-08-31 | August | Annual | Plan autumn audit and evidence collection sprint | GRC Lead / Internal Audit | ISO 27001, SOC 2, internal audit | Evidence collection plan | Medium | Planned | Reduce last-minute audit pressure.
2026-09-15 | September | Semi-annual | Run business continuity and crisis communication tabletop | BCM / CISO / Legal / Comms | DORA, NIS2, operational resilience | Exercise report and action plan | High | Planned | Include supplier breach scenario.
2026-09-30 | September | Quarterly | Prepare Q3 board report and budget/risk trade-off view | CISO / CIO | Board reporting, risk treatment | Board pack and risk decision list | High | Planned | Connect risks to investment decisions.
2026-10-15 | October | Annual | Review cyber insurance, contractual clauses, and supplier audit rights | Legal / Procurement / CISO | TPRM, DORA contractual requirements | Contractual control review | Medium | Planned | Prioritize critical ICT and data suppliers.
2026-10-31 | October | Quarterly | Review exceptions, accepted risks, and expiring risk decisions | Enterprise Risk / GRC Lead | Risk management, ISO 27001 clause 6 | Risk acceptance register | High | Planned | Escalate expired or repeatedly extended exceptions.
2026-11-15 | November | Annual | Refresh next-year GRC roadmap and maturity objectives | CISO / CIO / GRC Lead | Strategic planning | GRC roadmap draft | Medium | Planned | Use lessons from incidents and audits.
2026-11-30 | November | Annual | Confirm control testing plan for next year | GRC Lead / Internal Audit | ISO 27001, internal control system | Control testing plan | Medium | Planned | Align with audit and regulatory calendar.
2026-12-15 | December | Annual | Close annual risk review and confirm top residual risks | CISO / Enterprise Risk | Board governance, ISO 27001 management review | Annual risk review output | High | Planned | Feed into management review.
2026-12-31 | December | Annual | Prepare year-end cyber, resilience, and third-party risk summary | CISO / GRC Lead | Board reporting, annual reporting | Year-end executive summary | High | Planned | Use as input for January planning.

## Tool Backlog
Tool area | Example artifact | Use in practice | Audience | Publication status
Governance | Board cyber report template | Monthly or quarterly executive reporting | CISO, CIO, board secretary | Backlog
Metrics | Security KPI dashboard | Operational metrics with leadership context | CISO, SecOps, IT risk | Backlog
Third-party risk | Vendor risk register | Critical supplier tracking and review cadence | TPRM, procurement, CISO | Backlog
AI governance | AI use case and risk register | Shadow AI discovery and approval workflow | CIO, CISO, legal | Backlog
Incident response | Supplier breach response checklist | Clear actions when a vendor is compromised | CISO, legal, comms | Backlog
Audit readiness | ISO 27001 evidence tracker | Evidence ownership and audit preparation | ISMS manager, GRC | Backlog

## Cadence Model
Cadence | Typical activities | Recommended output | Leadership question answered
Monthly | Patch/vulnerability review, supplier watchlist, open findings aging | Operational exception summary | Where are we accumulating preventable risk?
Quarterly | Risk register update, board report, supplier tiering review, incident workflow check | Executive GRC pack | What decisions or escalations are needed?
Semi-annual | Access review, resilience tabletop, recovery evidence validation | Control assurance evidence | Can we prove the controls still work?
Annual | Risk appetite, policy refresh, control testing plan, year-end summary | Management review package | What should change next year?